## Gantt's Chart
Gantt's Chart | Date: 25.11.2023 | Creator: Johan Lossius
Semester Project 2, Noroff Frontend & UX, Year 2, deadline 4.2.2024
Semester Project 1
Start date: 25.11.2023 | Week 1: -> 26.11. | Week 2: -> 3.12. |  | Week 3: -> 10.12. |  | Week 4: -> 17.12. |  | Week 5: -> 24.12. |  | Week 6: -> 31.12. |  | Week 7: -> 7.1. |  | Week 8: -> 14.1. |  | Week 9: -> 21.1. |  | Week 10: -> 28.1. |  | Week 10: -> 4.2.
| Sat -> Sun | Mon -> Fri | Sat -> Sun | Mon -> Fri | Sat -> Sun | Mon -> Fri | Sat -> Sun | Mon -> Fri | Sat -> Sun | Mon -> Fri | Sat -> Sun | Mon -> Fri | Sat -> Sun | Mon -> Fri | Sat -> Sun | Mon -> Fri | Sat -> Sun | Mon -> Fri | Sat -> Sun | Mon -> Fri | Sat -> Sun
Projects
Trello Board
Gantt's Chart
Adobe xD Prototype Design
Style Guide
Code Infrastructure Setup
Build Out Web Layout
Style Page & Make Responsive
Build JS Functionality
QA / Review
Completion
Trello Board
Gantt's Chart
Adobe xD Prototype Design
Design Header
Design Footer
Design Front Page
Design Listings Feed
Design Profile Page
Design logged out functionality
Style Guide
Ideation; Colors, Typefaces, Icons, Logo, General Appearance, etc.
General Research Core Problem & Customer
Iterate on style elements to improve
Conclude on style guides, and complete the document
Code Infrastructure Setup
Github repo
Bootstrap
SASS
Bootstrap + SASS w/ Watch
GitHub Pages
Fully functional repo, integrated GitHub and VS Code
Build Out Web Layout
Add HTML and corresponding Bootstrap styles for a basic web layout
Style Page & Make Responsive
Work through the page with Bootstrap and SASS to make it styled, appealing, functional
Make the pages responsive
Build JS Functionality
1. A user with a stud.noroff.no email may register
2. A registered user may login
3. A registered user may logout
4. A registered user may update their avatar
5. A registered user may view their total credit
6. A registered user may create a Listing with a title, deadline date, media gallery and description
7. A registered user may add a Bid to another user’s Listing
8. A registered user may view Bids made on a Listing
9. An unregistered user may search through Listings
Optional: Build out any extra functions that time will allow
QA / Review
Review and build out remaining functionality across the page, to ensure marking critera and requirements are met
Document code | [17 empty] | *Could be more done
Modulate code
Complete Readme
Ensure hosting site is setup and works
Optional: Implement Jest and test out a few functions to ensure it works, to learn Jest properly
Optional: Implement Jest and test out a few functions to ensure it works, to learn Jest properly
Optional: Research and learn specific areas of knowledge gap that has been isolated in the process, and fill the gap
Optional: Ask tutor for coaching on specific areas of curiosity and / or uncertainty
Completion
Make final review that all requirements and demands are met
Turn in delivery
Continuous Delivery
Non Critical Task Main Project
Critical Path Main Project
Done Task
Slippage